## Sheet1
Risk # | Risk Description | Teamport_Sim_Description | Teamport_Sim_# | Mitigation Measures | Implementation in Teamport | Cost | Duration | Before_Likelihood | Before_Impact | Before_Risk Rank | After_Likelihood | After_Impact | After_Risk Rank
0 | Our Preferred Scenario from OS16 (1_3_10_3) | OS17_0 | 124 | No Risk Mitigation |  | 28527996 | 1733.1
1 | System Integration Risk: Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1 | 129 | Increase Work Effort for Arch. Refinement; High Concurrency between FCS - H2 Team | Increase Scope(Work Effort) for Architecture Refinement (60W->70W); Increase Concurrency among dependent teams (FCS-H2) | 28895839 | 1746.1 | L-7 | I-8 | 5 | L-6 | I-7 | 3 | 7 | 8 | 15 | 6 | 7 | 13 | 6.5 | 7.5 | 14.5 | 5.5 | 6.5 | 12.5
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_1 | 130 | Increase concurrency between Arch. Refinement and Design Activities | Increased concurrency between Arch Refinement and design activitie | 29041320 | 1701.6 | L-7 | I-8 | 5 | L-6 | I-8 | 4 | 7 | 8 | 15 | 6 | 8 | 14 | 6.5 | 7.5 | 14.5 | 5.5 | 7.5 | 13.5
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_2 | 131 | Increase Work Effort for Arch Refinement and Design Review; Increase Resources for Teams | Increased Work Effort for Arch Definement and Design Review(80W); Increase Aero and SE team to 40 each | 30462718 | 1617.1 | L-7 | I-8 | 5 | L-4 | I-7 | 3 | 7 | 8 | 15 | 4 | 7 | 11 | 6.5 | 7.5 | 14.5 | 3.5 | 6.5 | 10.5
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_3 | 132 | Enhance collaboration between design teams for Quality assurance | Checked "Q" - Quality for design activities to involve various teams | 30433112 | 1591.1 | L-7 | I-8 | 5 | L-6 | I-7 | 4 | 7 | 8 | 15 | 6 | 7 | 13 | 6.5 | 7.5 | 14.5 | 5.5 | 6.5 | 12.5
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_4 | 133 | Add Scope for Planned Rework (More iterations) | Added Planned Rework by increasing Work Effort for Refinements (100W) | 30759460 | 1619.8 | L-7 | I-8 | 5 | L-5 | I-5 | 2 | 7 | 8 | 15 | 5 | 5 | 10 | 6.5 | 7.5 | 14.5 | 4.5 | 4.5 | 9.5
2 | Volatility in Labor Costs due to centralized geographical teams | OS17_2 | 135 | Diversify Locations of Teams | Created new locations (Korea, Perth - $100/hr) and assigned FCS/HEX/Battery teams to new locations outside of Europe | 26445313 | 1742.8 | L-8 | I-5 | 5 | L-5 | I-3 | 3 | 8 | 5 | 13 | 5 | 3 | 8 | 7.5 | 4.5 | 12.5 | 4.5 | 2.5 | 7.5
| Volatility in Labor Costs due to centralized geographical teams | OS17_2_1 | 136 | Diversify Locations of Teams with the same rate | Set the same rate for Korean and Perth as European teams ($180/hr) | 28743314 | 1732.3 | L-8 | I-5 | 5 | L-3 | I-4 | 4 | 8 | 5 | 13 | 3 | 4 | 7 | 7.5 | 4.5 | 12.5 | 2.5 | 3.5 | 6.5
| Volatility in Labor Costs due to centralized geographical teams | OS17_2_2 | 137 | Diversify Locations, Reflect the increased complexity in communiating with different teams | Increase Work Effort for Arch Refinement (80W, Med-High Complexity) | 29150950 | 1760.8 | L-8 | I-5 | 5 | L-3 | I-2 | 2 | 8 | 5 | 13 | 3 | 2 | 5 | 7.5 | 4.5 | 12.5 | 2.5 | 1.5 | 4.5
3 | Labor Strike in One Team (Manufacturing, etc.) | OS17_3 | 139 | Shuffle people between internal teams (cross-training) so they can take on different tasks | Add multiple internal teams to do Quality / Assistance roles for Production Tooling & manufacturing | 29794043 | 1413.8 | L-2 | I-8 | 4 | L-2 | I-4 | 3 | 2 | 8 | 10 | 2 | 4 | 6 | 1.5 | 7.5 | 9.5 | 1.5 | 3.5 | 5.5
4 | Critical Design Review Discovery | OS17_4 | 141 | Add external consultants for design review; Added scope (work effort) | Added a new team (ext_DesignReview) for Design Review Tasks with high efficiency in review/design tasks; Increased Work Effort for Design Review from 60W to 100W | 29558726 | 1850.3 | L-5 | I-9 | 5 | L-3 | I-5 | 3 | 5 | 9 | 14 | 3 | 5 | 8 | 4.5 | 8.5 | 13.5 | 2.5 | 4.5 | 7.5
5 | Global Pandemic - Supply Chain Impacted | OS17_5 | 143 | Added a new internal team (resources) to enable remote work | Added a new team(Remote Work) and assigned Assist role for most of the tasks | 28455782 | 1703 | L-2 | I-8 | 4 | L-2 | I-5 | 2 | 2 | 8 | 10 | 2 | 5 | 7 | 1.5 | 7.5 | 9.5 | 1.5 | 4.5 | 6.5
|  | OS17_5_1 | 144 | Added a buffer to represent delay in external supplier (supply chain) | Added a buffer tasks in the System Design phase (10W) and assigned Remote Work Team as P | 27844108 | 1689 | L-2 | I-8 | 4 | L-2 | I-5 | 2 | 2 | 8 | 10 | 2 | 5 | 7 | 1.5 | 7.5 | 9.5 | 1.5 | 4.5 | 6.5
|  | OS17_5_2 | 145 | Adjusted Remote Work Team Rate ($150/hr) and Remote Work Buffer (30W) |  | 28929948 | 1712 | L-2 | I-8 | 4 | L-2 | I-3 | 2 | 2 | 8 | 10 | 2 | 3 | 5 | 1.5 | 7.5 | 9.5 | 1.5 | 2.5 | 4.5
1+3 (C1) | System Design Rework + Labor | OS17_Combined_1_3 | 148 | Mitigated System Design Risk with added team resource cross-training/allocation | OS17_1_4 + OS17_3 | 32354303 | 1186 | L-7 | I-8 | 5 | L-2 | I-2 | 2 | 7 | 8 | 15 | 2 | 2 | 4 | 6.5 | 7.5 | 14.5 | 1.5 | 1.5 | 3.5
1+3+4 (C2) | SyStem Design Rework + Labor + External Design Review (Added Resources) - This combined mitigation measures for Risk 1, 4, 11 | OS17_Combined_1_3_4 | 151 | Combined 1+3+4 | OS17_1_4 + OS17_3 + OS17_4; Increased Design Review Scope to 120W; Arch Refinement 120W; Design Review Team 8 | 32630501 | 1198.8 | L-8 | I-9 | 5 | L-3 | I-2 | 2 | 8 | 9 | 17 | 3 | 2 | 5 | 7.5 | 8.5 | 16.5 | 2.5 | 1.5 | 4.5
6 | System Failure due to subsystem incompatibility, component interface failure, or other unknown-unknown related to total product architecture. | OS17_6 | 158 | Increase SE team & add additional coordination and overlap between Ses and between connected vendor components |  | 30222076 | 1763.3 | L-4 | I-9 |  | L-2 | I-6 |  | 4 | 9 | 13 | 2 | 6 | 8 | 3.5 | 8.5 | 12.5 | 1.5 | 5.5 | 7.5
7 | Early to market Competitor | OS17_7 | 160 | Increase External Vendor Resources for Design Phase | * May need to revisit this one not much change | 28149079 | 1704.2 | L-5 | I-5 |  | L-4 | I-2 |  | 5 | 5 | 10 | 4 | 2 | 6 | 4.5 | 4.5 | 9.5 | 3.5 | 1.5 | 5.5
8 | Low TRL maturity for longer time

## Sheet1_Copy
Risk # | Risk Description | Teamport_Sim_Description | Teamport_Sim_# | Mitigation Measures | Implementation in Teamport | Cost | Duration | Before_Likelihood | Before_Impact | Before_Risk Rank | After_Likelihood | After_Impact | After_Risk Rank
0 | Our Preferred Scenario from OS16 (1_3_10_3) | OS17_0 | 124 | No Risk Mitigation |  | 28527996 | 1733.1
1 | System Integration Risk: Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1 | 129 | Increase Work Effort for Arch. Refinement; High Concurrency between FCS - H2 Team | Increase Scope(Work Effort) for Architecture Refinement (60W->70W); Increase Concurrency among dependent teams (FCS-H2) | 28895839 | 1746.1 | L-2 | I-3 | 5 | L-1 | I-2 | 3
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_1 | 130 | Increase concurrency between Arch. Refinement and Design Activities | Increased concurrency between Arch Refinement and design activitie | 29041320 | 1701.6 | L-2 | I-3 | 5 | L-2 | I-2 | 4
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_2 | 131 | Increase Work Effort for Arch Refinement and Design Review; Increase Resources for Teams | Increased Work Effort for Arch Definement and Design Review(80W); Increase Aero and SE team to 40 each | 30462718 | 1617.1 | L-2 | I-3 | 5 | L-1 | I-2 | 3
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_3 | 132 | Enhance collaboration between design teams for Quality assurance | Checked "Q" - Quality for design activities to involve various teams | 30433112 | 1591.1 | L-2 | I-3 | 5 | L-2 | I-2 | 4
| Unexpected delays and rework in System Integration with External teams due to low concurrency between design activities and refinement | OS17_1_4 | 133 | Add Scope for Planned Rework (More iterations) | Added Planned Rework by increasing Work Effort for Refinements (100W) | 30759460 | 1619.8 | L-2 | I-3 | 5 | L-1 | I-1 | 2
2 | Volatility in Labor Costs due to centralized geographical teams | OS17_2 | 135 | Diversify Locations of Teams | Created new locations (Korea, Perth - $100/hr) and assigned FCS/HEX/Battery teams to new locations outside of Europe | 26445313 | 1742.8 | L-3 | I-2 | 5 | L2 | I-1 | 3
| Volatility in Labor Costs due to centralized geographical teams | OS17_2_1 | 136 | Diversify Locations of Teams with the same rate | Set the same rate for Korean and Perth as European teams ($180/hr) | 28743314 | 1732.3 | L-3 | I-2 | 5 | L-2 | I-2 | 4
| Volatility in Labor Costs due to centralized geographical teams | OS17_2_2 | 137 | Diversify Locations, Reflect the increased complexity in communiating with different teams | Increase Work Effort for Arch Refinement (80W, Med-High Complexity) | 29150950 | 1760.8 | L-3 | I-2 | 5 | L-1 | I-1 | 2
3 | Labor Strike in One Team (Manufacturing, etc.) | OS17_3 | 139 | Shuffle people between internal teams (cross-training) so they can take on different tasks | Add multiple internal teams to do Quality / Assistance roles for Production Tooling & manufacturing | 29794043 | 1413.8 | L-1 | I-3 | 4 | L-1 | I-2 | 3
4 | Critical Design Review Discovery | OS17_4 | 141 | Add external consultants for design review; Added scope (work effort) | Added a new team (ext_DesignReview) for Design Review Tasks with high efficiency in review/design tasks; Increased Work Effort for Design Review from 60W to 100W | 29558726 | 1850.3 | L-2 | I-3 | 5 | L-1 | I-2 | 3
5 | Global Pandemic - Supply Chain Impacted | OS17_5 | 143 | Added a new internal team (resources) to enable remote work | Added a new team(Remote Work) and assigned Assist role for most of the tasks | 28455782 | 1703 | L-1 | I-3 | 4 | L-1 | I-1 | 2
|  | OS17_5_1 | 144 | Added a buffer to represent delay in external supplier (supply chain) | Added a buffer tasks in the System Design phase (10W) and assigned Remote Work Team as P | 27844108 | 1689 | L-1 | I-3 | 4 | L-1 | I-1 | 2
|  | OS17_5_2 | 145 | Adjusted Remote Work Team Rate ($150/hr) and Remote Work Buffer (30W) |  | 28929948 | 1712 | L-1 | I-3 | 4 | L-1 | I-1 | 2
1+3 (C1) | System Design Rework + Labor | OS17_Combined_1_3 | 148 | Mitigated System Design Risk with added team resource cross-training/allocation | OS17_1_4 + OS17_3 | 32354303 | 1186 | L-2 | I-3 | 5 | L-1 | I-1 | 2
1+3+4 (C2) | SyStem Design Rework + Labor + External Design Review (Added Resources) - This combined mitigation measures for Risk 1, 4, 11 | OS17_Combined_1_3_4 | 151 | Combined 1+3+4 | OS17_1_4 + OS17_3 + OS17_4; Increased Design Review Scope to 120W; Arch Refinement 120W; Design Review Team 8 | 32630501 | 1198.8 | L-2 | I-3 | 5 | L-1 | I-1 | 2
6 | System Failure due to subsystem incompatibility, component interface failure, or other unknown-unknown related to total product architecture. | OS17_6 | 158 | Increase SE team & add additional coordination and overlap between Ses and between connected vendor components |  | 30222076 | 1763.3
7 | Early to market Competitor | OS17_7 | 160 | Increase External Vendor Resources for Design Phase | * May need to revisit this one not much change | 28149079 | 1704.2
8 | Low TRL maturity for longer time

## Risk Matrix
Simulation | Before Likelihood | Before Impact | Before Risk | After Likelihood | After Impact | After Risk | Risk Mitigation | Cost | Duration | Duration (Years)
OS16_1_3_10 | 9 | 9 | 18 | 9 | 9 | 18 | Baseline (No Risk Mitigation) | 28527996 | 1733.1 | 4.7482
OS17_1 | 7 | 8 | 15 | 6 | 7 | 13 | Risk 1 (System Integration Risk) | 28895839 | 1746.1 | 4.7838
OS17_1_1 | 7 | 8 | 15 | 6 | 8 | 14 | Risk 1 (System Integration Risk) | 29041320 | 1701.6 | 4.6619
OS17_1_2 | 7 | 8 | 15 | 4 | 7 | 11 | Risk 1 (System Integration Risk) | 30462718 | 1617.1 | 4.4304
OS17_1_3 | 7 | 8 | 15 | 6 | 7 | 13 | Risk 1 (System Integration Risk) | 30433112 | 1591.1 | 4.3592
OS17_1_4 | 7 | 8 | 15 | 5 | 5 | 10 | Risk 1 (System Integration Risk) | 30759460 | 1619.8 | 4.4378
OS17_2 | 8 | 5 | 13 | 5 | 3 | 8 | Risk 2 (Volatility in Labor Costs) | 26445313 | 1742.8 | 4.7748
OS17_2_1 | 8 | 5 | 13 | 3 | 4 | 7 | Risk 2 (Volatility in Labor Costs) | 28743314 | 1732.3 | 4.746
OS17_2_2 | 8 | 5 | 13 | 3 | 2 | 5 | Risk 2 (Volatility in Labor Costs) | 29150950 | 1760.8 | 4.8241
OS17_3 | 2 | 8 | 10 | 2 | 4 | 6 | Risk 3 (Labor Strike) | 29794043 | 1413.8 | 3.8734
OS17_4 | 5 | 9 | 14 | 3 | 5 | 8 | Risk 4 (Critial Design Review Rework) | 29558726 | 1850.3 | 5.0693
OS17_5 | 2 | 8 | 10 | 2 | 5 | 7 | Risk 5 (Global Pandemic -Supply Chain Impacted) | 28455782 | 1703 | 4.6658
OS17_5_1 | 2 | 8 | 10 | 2 | 5 | 7 | Risk 5 (Global Pandemic -Supply Chain Impacted) | 27844108 | 1689 | 4.6274
OS17_5_2 | 2 | 8 | 10 | 2 | 3 | 5 | Risk 5 (Global Pandemic -Supply Chain Impacted) | 28929948 | 1712 | 4.6904
OS17_Combined_1_3 | 7 | 8 | 15 | 2 | 2 | 4 | Combined (1+3) | 32354303 | 1186 | 3.2493
OS17_Combined_1_3_4 | 8 | 9 | 17 | 3 | 2 | 5 | Combined (1+3+4) | 32630501 | 1198.8 | 3.2844
OS17_6 | 4 | 9 | 13 | 2 | 6 | 8 | Risk 6 (System Failure due to unk unk) | 30222076 | 1763.3 | 4.831
OS17_7 | 5 | 5 | 10 | 4 | 2 | 6 | Risk 7 (Losing Market Share due to competitors) | 28149079 | 1704.2 | 4.669